## Slide 1
Seasonal Malaria Chemoprevention (SMC)
2023 Campaign
Ghana
Dr. Dora Dadzie
Prepared for the 2024 SMC Alliance Meeting – Abuja, Nigeria

## Slide 2
Summary information for 2023 and plans for 2024 campaigns
 | 2023 | 2024
Start and end dates | 26th June – 2nd December | 18th June – 9th November
Number of cycles | 4 | 5
Number of districts targeted | 69 (72) | 69 (72)
Number of children covered | 1,497,595 reached | 1,549,854
Age ranges covered | 3 – 59 months | 3 – 59 months
Coverage (% targeted children receiving all cycles) | 85.8% | N/A
Any drug resistance testing or efficacy studies performed? | No | No
Any gap | Insufficient funding | Insufficient funding
Notes: 2023 Target: 1,439,398
104%

## Slide 3
2023 map (covered)
2024 map (targets)
Country map showing SMC implementing districts

## Slide 4
Focus Reaching Hard-to-Reach Populations
Navigating SMC Implementation amidst Ethnic Conflict

## Slide 5
Key lessons learnt in 2023: Reaching hard-to-reach populations
Longstanding territorial dispute between two ethnic groups in Bawku, Upper East region, Ghana
Periodic and unpredictable escalation of conflict resulting in insecurity, loss of lives, people displacement, property destruction (including health infrastructure)
Security risks for health workers & volunteers
Limited access to eligible population
Lowest SMC coverage in the region (75.8% compared with regional avg. of 85.5%– receiving 4 doses)
Limited oversight of campaign activities by supervisors
Background

## Slide 6
Key lessons learnt / innovation in 2023: Reaching hard-to-reach populations
Engagement with local community and authorities (including political heads and security agency)
Health worker trainings conducted in far districts to prevent violent clashes
Special considerations in volunteer and supervisor recruitment: number, ethnicity etc.
Flexibility in dosing days
Use of IT to conduct targeted supervision: monitoring daily coverage
Movement of commodities and personnel in only GHS branded vehicles
Caution to volunteer & supervisors to not cross territory
Innovation

## Slide 7
Key lessons learnt in 2023: Reaching hard-to-reach populations
Unstable size of target population
Limited access to public health facilities for ADR management (District referral hospital not accessible to one faction)
Extra cost (funding not adequate)
Curfew limits access to target population (impedes option to reach families early morning and evening)
Limited information/guidance on implementing SMC/public health interventions in conflict areas
No clear protocols on ensuring safety of volunteers and supervisors
Challenges

## Slide 8
Key lessons learnt in 2023: Reaching hard-to-reach populations
Improve resource allocation to the district
Consider additional distribution strategy (e.g. fixed point)
Liaise with relevant agencies to develop clear protocols for ensuring safety of volunteers and supervisors
Equip volunteers and supervisors with knowledge and skills needed for working in a conflict area
Liaise with private facilities to provide free care for children with ADRs
Future activities

## Slide 9: Thank you